## Sheet1
Step | Operation | Project Duration
|  | 2016 | [19 empty] | 2017
|  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Analyze and determine the requirements of the project | bar: August 1 to August 2
2 | Plan the project schedule | bar: August 2 to August 3
3 | Work on introduction chapter of the report (chapter 1) | bar: August 2 to August 3
4 | Research emphasizing on the following topics: | bar: August 2 to September 2
1) Work by other researchers on discriminating between similar images using machine learning | bar: August 2 to August 3
2) ML method for image classification especially CNN and the available libraries | bar: August 4 to September 1
3) Basic image processing concept | bar: September 2
5 | Create the project proposal and get feedbacks | bar: September 2
6 | Test prototypes for various learning frameworks and make a decision on which learning framework to use | bar: September 3 to September 4
7 | Collect and create dataset | bar: October 1
8 | Study and understand the dataset | bar: October 1
9 | Create experimental design | bar: October 2
10 | Complete progress report for the first semester | bar: October 3
11 | Prepare for presentation for the first semester | bar: October 3
12 | Work on background and theory chapter of the report (chapter 2) | bar: November 1
13 | Work on methodology chapter of the report (chapter 3) | bar: November 3
14 | Write pre-processing software to standardize images | bar: November 4 to January 1
15 | Write scripts to control the experiments | bar: January 2 to January 3
16 | Test the system and fix bugs | bar: January 4 to February 2
17 | Train and test the system with different parameters | bar: February 3 to April 1
18 | Analyze the results | bar: April 2 to April 3
19 | Complete final report for the second semester (Result + conclusions, chapter 4 and 5) | bar: April 4
20 | Create poster and prepare for presentation for the second semester | bar: April 4